# Execution Workbook

Netropy VE Automated Provisioning Internship

Based on the Netropy VE Provisioning Intern Project requirements

# How to use this workbook

You own the hands-on execution of this project. You are expected to perform the research, create the repository, install and verify the tools, write the code, run the tests, document the results, and demonstrate each phase. The mentor provides access, guidance, review, risk controls, and phase approval, but should not do the implementation for you. Work through one phase at a time, attach evidence to the repository or pull request, and record verified facts separately from assumptions. AI tools are assistants: you remain responsible for understanding, reviewing, and testing everything they generate.

| Item | Details |
| --- | --- |
| Project goal | Build a command-line tool that reads one JSON file and creates a Netropy VE VM plus two Ubuntu traffic endpoints on KVM, ESXi, or AWS. |
| Network topology | One management subnet shared by all three VMs, one data subnet between Linux-1 and Netropy data port 1, and one data subnet between Netropy data port 2 and Linux-2. |
| Implementation direction | OpenTofu modules per platform, cloud-init for Ubuntu, and a thin Python CLI for validation and orchestration. |
| First implementation target | KVM/libvirt. |
| Definition of success | Provision, access, verify traffic through Netropy, re-run idempotently, and destroy with single-command workflows. |

# Rules for using Cursor or Codex

☐ Ask the AI to inspect AGENTS.md and relevant files first.

☐ Give one narrow task per prompt.

☐ Ask for a plan, assumptions, files to change, tests, and risks before implementation.

☐ Use investigation-only prompts before asking for a fix.

☐ Never paste production credentials, access keys, passwords, or private keys.

☐ Review diffs and commands before execution.

☐ Require tests and a final section labeled Verified, Assumed, Unknown, and Needs Product Confirmation.

☐ Do not accept a success claim without running the acceptance test yourself.

# Reusable AI prompt

Read AGENTS.md, README.md, docs/architecture.md, and the relevant files. Current task: [ONE NARROW TASK]. Do not expand scope, invent Netropy behavior, expose secrets, or run destructive commands without explaining them. Before editing, provide your understanding, files inspected, assumptions, proposed files, implementation steps, tests, and risks. After implementation, list files changed, commands run, test results, manual verification, verified facts, assumptions, and recommended next task.

# Phase 1 — Understand the Lab and Networking Fundamentals

| Suggested duration 3–5 days | Primary deliverable One-page architecture note, topology diagram, seven-NIC table, and open-question list. | Exit gate Student explains the packet path and role of every NIC without reading the brief. |
| --- | --- | --- |

## Student execution checklist

☐ Explain the purpose of the Netropy VE lab in plain language.

☐ Draw the management, data-1, and data-2 networks.

☐ Identify all seven VM interfaces and their subnet membership.

☐ Explain the traffic path from Linux-1 through Netropy to Linux-2.

☐ Practice ip addr, ip link, ip route, ping, ssh, and iperf3.

☐ Explain bridge mode versus routed mode at a beginner level.

☐ List all Netropy-specific questions that require product-team confirmation.

## Required learning and reading

☐ KVM/QEMU/libvirt overview

☐ IPv4 subnets, CIDR, gateways, and routing

☐ Linux network-interface and route commands

☐ iperf3 client/server basics

☐ Conceptual introduction to DPDK/UIO and userspace NIC binding

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Phase 2 — Set Up the Development Environment and Repository

| Suggested duration 2–3 days | Primary deliverable Working repository with documented setup, agent instructions, and reproducible developer environment. | Exit gate A fresh shell can run the documented setup checks successfully. |
| --- | --- | --- |

## Student execution checklist

☐ Create the Git repository and document the mentor-approved branch strategy.

☐ Install and verify Python, virtual environment tooling, OpenTofu, KVM/libvirt tools, and cloud-init utilities on the approved development host.

☐ Create the recommended repository structure and explain the purpose of each top-level directory.

☐ Draft and add AGENTS.md and Cursor/Codex project rules, then submit them for mentor review.

☐ Implement secret-handling, state-file, private-key, and destructive-command guardrails.

☐ Write the baseline README and create the first clean commit and baseline tag.

☐ Create or import a basic libvirt VM and demonstrate how to start, inspect, stop, and destroy it.

## Required learning and reading

☐ Git basics and small pull requests

☐ Python virtual environments

☐ OpenTofu CLI basics

☐ libvirt and virsh basics

☐ How Cursor/Codex reads repository instructions

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Phase 3 — Research and Validate the Tool Selection

| Suggested duration 1–2 weeks | Primary deliverable Two-to-four-page recommendation and a one-VM KVM proof-of-concept. | Exit gate Mentor approves the tool choice and no blocking provider limitation remains for KVM. |
| --- | --- | --- |

## Student execution checklist

☐ Compare OpenTofu, Terraform, Pulumi, platform-native tools, cloud-init, and Ansible.

☐ Verify current provider health for libvirt, vSphere, and AWS.

☐ Create one Ubuntu VM on KVM using OpenTofu.

☐ Use cloud-init to create a user, add an SSH key, and install iperf3.

☐ Expose the VM management IP as an OpenTofu output.

☐ Destroy the proof-of-concept cleanly.

☐ Record verified facts, assumptions, risks, and open questions.

## Required learning and reading

☐ OpenTofu configuration, providers, variables, state, outputs

☐ cloud-init NoCloud concepts

☐ libvirt provider documentation

☐ vSphere and AWS provider capability review

☐ Basic infrastructure-as-code idempotence

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Phase 4 — Define the JSON Configuration Contract

| Suggested duration 3–4 days | Primary deliverable The validate command and a comprehensive test suite for configuration errors. | Exit gate Invalid input fails early with a precise field-level message; valid input produces a normalized summary. |
| --- | --- | --- |

## Student execution checklist

☐ Define required and optional JSON fields.

☐ Create a JSON Schema.

☐ Implement typed Python configuration models.

☐ Validate platform, CIDRs, IP membership, duplicate addresses, overlap, file paths, CPU, memory, and SSH keys.

☐ Create valid and invalid sample files.

☐ Add unit tests for every validation rule.

☐ Ensure validation performs no provisioning.

## Required learning and reading

☐ JSON Schema fundamentals

☐ Python type models and validation

☐ ipaddress module

☐ Actionable CLI error design

☐ Secret references through environment variables or profiles

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Phase 5 — Build the Complete KVM Lab Incrementally

| Suggested duration 2–3 weeks | Primary deliverable A complete KVM three-VM lab created from configuration and destroyed repeatably. | Exit gate All KVM acceptance criteria pass, including traffic through Netropy and idempotent re-apply. |
| --- | --- | --- |

## Student execution checklist

☐ Create the three libvirt networks.

☐ Provision Linux-1 with management and data-1 NICs.

☐ Provision Linux-2 with management and data-2 NICs.

☐ Configure static addresses through cloud-init.

☐ Install and verify iperf3 on both Linux VMs.

☐ Confirm Netropy image format, boot mode, resource minimums, NIC model, and NIC order.

☐ Provision Netropy with management, data-1, and data-2 NICs.

☐ Reach both Linux hosts and Netropy management.

☐ Configure Netropy manually in bridge or routed mode.

☐ Run traffic through Netropy and observe an emulation effect.

☐ Re-run apply and confirm no duplicate resources.

☐ Destroy the entire lab cleanly.

## Required learning and reading

☐ libvirt networks and bridges

☐ Multi-NIC cloud-init configuration

☐ OpenTofu modules and outputs

☐ Netropy VE product documentation

☐ iperf3 and ping-based data-path testing

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Phase 6 — Build the Python CLI Wrapper

| Suggested duration 1 week | Primary deliverable A single-command user experience around the tested KVM modules. | Exit gate A user can create and destroy the KVM lab without directly invoking OpenTofu. |
| --- | --- | --- |

## Student execution checklist

☐ Implement validate, plan, create, status, verify, and destroy commands.

☐ Select the platform module from the JSON.

☐ Generate machine-readable variable input without rewriting infrastructure source files.

☐ Run OpenTofu safely without shell=True.

☐ Isolate state per lab.

☐ Redact secrets from console output and logs.

☐ Parse OpenTofu outputs and print an access summary.

☐ Add unit tests using mocked subprocess execution.

☐ Return useful errors while preserving a sanitized debug log.

## Required learning and reading

☐ Python CLI frameworks

☐ subprocess safety

☐ OpenTofu JSON output

☐ State-directory design

☐ Logging and secret redaction

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Phase 7 — Add Verification and Failure Diagnostics

| Suggested duration 3–5 days | Primary deliverable A verify command with clear PASS, FAIL, and NOT READY results plus diagnostics. | Exit gate The tool identifies the failed layer instead of only reporting that provisioning failed. |
| --- | --- | --- |

## Student execution checklist

☐ Verify expected VMs, networks, and NIC counts.

☐ Verify management reachability.

☐ Verify SSH and cloud-init completion.

☐ Verify addresses and routes inside both Linux VMs.

☐ Verify iperf3 is installed.

☐ Distinguish infrastructure-ready from Netropy-forwarding-ready.

☐ Create a sanitized failure bundle.

☐ Provide next-action guidance for common failures.

## Required learning and reading

☐ Layered troubleshooting methodology

☐ SSH automation

☐ virsh inspection commands

☐ cloud-init logs

☐ Network path and route diagnostics

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Phase 8 — Add ESXi/vSphere as the Second Platform

| Suggested duration 1–2 weeks | Primary deliverable The same JSON-driven workflow succeeds on vSphere with a separate platform module. | Exit gate ESXi passes the equivalent Phase-1 acceptance tests without breaking KVM. |
| --- | --- | --- |

## Student execution checklist

☐ Document the KVM-to-vSphere concept mapping.

☐ Confirm access, datastore, network, permissions, and image workflow.

☐ Deploy one Ubuntu VM and verify cloud-init.

☐ Create or select three port groups.

☐ Deploy both Linux endpoints.

☐ Deploy Netropy from the approved image workflow.

☐ Confirm NIC model and deterministic NIC order.

☐ Run the same management and data-path tests.

☐ Keep the CLI output consistent with KVM.

☐ Document platform-specific limitations.

## Required learning and reading

☐ vSphere inventory and permissions

☐ Port groups and distributed/standard switches

☐ OVA/OVF or template deployment

☐ VMXNET3 and guest customization

☐ vSphere provider concepts

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Phase 9 — Add AWS and Document Cloud Differences

| Suggested duration 1–2 weeks | Primary deliverable An AWS implementation or a documented limitation report for any requirement that cannot be reproduced exactly. | Exit gate Mentor approves the AWS interpretation and all created resources are private, tagged, and destroyable. |
| --- | --- | --- |

## Student execution checklist

☐ Resolve the Netropy AMI or image-import workflow.

☐ Select supported instance types and ENI counts.

☐ Create isolated management, data-1, and data-2 subnets.

☐ Attach ENIs in deterministic order where supported.

☐ Keep data interfaces private.

☐ Use roles or profiles instead of access keys in JSON.

☐ Tag all resources with owner, lab, and lifecycle metadata.

☐ Add cost and exposure warnings.

☐ Run the same verification workflow where technically meaningful.

☐ Document how single-host and passthrough semantics differ in EC2.

## Required learning and reading

☐ VPC, subnets, route tables, security groups, and ENIs

☐ EC2 image import and AMIs

☐ IAM roles and profiles

☐ AWS provider state and teardown

☐ Cloud-specific topology limitations

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Phase 10 — Stabilize, Document, Demonstrate, and Consider Passthrough

| Suggested duration 1–2 weeks | Primary deliverable Release-ready repository, documentation, demo, and optional passthrough investigation. | Exit gate A new user can follow the README to build, verify, and destroy the lab. |
| --- | --- | --- |

## Student execution checklist

☐ Complete README and per-platform prerequisites.

☐ Document the JSON reference and secret handling.

☐ Document build, verify, troubleshoot, and destroy workflows.

☐ Record tested versions and known limitations.

☐ Run the complete demo from a clean starting point.

☐ Demonstrate idempotent re-run and clean teardown.

☐ Create handover notes and a backlog.

☐ Attempt passthrough only after Phase 1 is stable and hardware support is confirmed.

☐ For passthrough, document IOMMU, VFIO/SR-IOV, device ownership, and host bridge design.

☐ Prepare a final presentation or live demo script.

## Required learning and reading

☐ Technical documentation

☐ Release checklists

☐ Demo preparation

☐ IOMMU/VFIO/SR-IOV fundamentals for stretch work

☐ Operational handoff

## Student evidence to attach

☐ Notes or short summary of what was learned.

☐ Commands used and relevant output, with secrets removed.

☐ Git commit or pull-request link for implementation work.

☐ Test results and screenshots where useful.

☐ Verified facts, assumptions, open questions, and mentor decisions needed.

## Student self-check

☐ I can explain this phase's work in my own words.

☐ I reviewed every AI-generated file and command.

☐ I did not commit credentials or private keys.

☐ I tested the stated acceptance criteria.

☐ I recorded anything that remains uncertain.

Student completion: Name: ____________________   Date: __________   Commit/PR: ____________________

# Final student demonstration checklist

☐ Start with no lab resources present.

☐ Run JSON validation and explain the normalized configuration.

☐ Run plan and describe the resources to be created.

☐ Create the complete lab.

☐ SSH to Linux-1 and Linux-2.

☐ Reach Netropy management.

☐ Show interface and route configuration.

☐ Run baseline traffic through Netropy.

☐ Apply an emulation setting and show the observable effect.

☐ Re-run create/apply and show idempotence.

☐ Run verify and explain each result.

☐ Destroy the lab and confirm all resources are removed.

☐ Explain known limitations and next steps.

# Final reflection

What did I learn about infrastructure as code?

______________________________________________________________________________________________________________

What did I learn about Linux networking and multi-NIC VMs?

______________________________________________________________________________________________________________

Which assumptions caused the most rework?

______________________________________________________________________________________________________________

How did I verify AI-generated code?

______________________________________________________________________________________________________________

What would I redesign in a second version?

______________________________________________________________________________________________________________

Source: Netropy-VE-Provisioning-Intern-Project requirements specification supplied for this internship project.